## Timeline
Tasks
Start | End | Duration(days) | Objectives | Vert. Position | Vert. Line
2020-04-22 | 2020-05-05 | 14 | Understand the calibration model and learn the theory | -20 | -20
2020-04-29 | 2020-05-12 | 14 | Learn the R language | -35 | -15
2020-05-06 | 2020-05-12 | 7 | Understand the model code | -50 | -15
2020-05-13 | 2020-05-27 | 15 | Prepare some of the dataset and try to get the results from the model | -65 | -65
2020-05-28 | 2020-06-03 | 7 | Reflection and conclusion | -80 | -80
2020-06-04 | 2020-06-24 | 21 | Get all the results and data | -95 | -15
2020-06-25 | 2020-07-08 | 14 | Compare the results and get some plots | -20 | -20
2020-07-09 | 2020-07-15 | 7 | Documentation and conclusion | -60 | -40
2020-07-16 | 2020-08-26 | 42 | Write the paper | -75 | -15
Milestones
Date |  |  | Label | Position
2020-04-22 |  |  | Start, Apr 22 | 30
2020-05-12 |  |  | Milestone #1 ,May.12 (Move to the data process step) | 15
2020-06-24 |  |  | Milestone #2 ,Jun. 24 (Start to write the paper) | 15
2020-08-26 |  |  | End of the Summer Break, Aug 26 | 30
Formulas:
End = [Start]+[Duration(days)]-1

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.